## Overview
Sports Hall Booking System – ServiceNow Development Plan
Task tracker generated from project requirements document
Project | Sports Hall Booking System (ServiceNow Service Portal)
Purpose | Enable self-service booking of sports facility slots with automated approvals, notifications, and status tracking.
Phases | 4 (Requirements & Planning, Backend Development & Configuration, UI/UX Development, Data Migration/Testing/Security)
How to use this file | Each phase has its own tab listing all development tasks. Update Owner, Status, and Effort columns as work progresses. Use the 'All Tasks' tab for a master consolidated view and filtering.
Status Legend
Not Started
In Progress
Blocked
Complete

## All Tasks
Task ID | Phase | Workstream | Task | Description / Acceptance Criteria | Owner Role | Priority | Estimated Effort (days) | Dependencies | Status
T001 | Phase 1 | Business Objectives | Define business objectives & success metrics | Document goals: self-service booking, reduced admin overhead, improved facility utilization. Define KPIs (e.g., usage %, satisfaction score). | Business Analyst | High | 2 | - | Not Started
T002 | Phase 1 | Business Objectives | Define booking policy rules | Agree scope rules such as max advance booking window (X days), booking limits per user, cancellation windows. | Business Analyst / Sponsor | High | 1 | Define business objectives | Not Started
T003 | Phase 1 | Functional Scope | Compile functional requirements list | Document all required features: facility search/browse, real-time availability calendar, booking form, multi-stage approval, notifications, My Bookings (view/cancel/modify), admin console. | Business Analyst | High | 3 | Define business objectives | Not Started
T004 | Phase 1 | Functional Scope | Prioritize features into MVP vs later phases | Rank features by business value and feasibility; agree MVP scope for go-live. | Product Owner | Medium | 1 | Compile functional requirements list | Not Started
T005 | Phase 1 | Stakeholder Mapping | Identify roles and permissions matrix | Map roles: end-users (students/staff), facility managers/approvers, system administrators, IT support. Document needs, permissions, and RACI. | Business Analyst | High | 2 | Compile functional requirements list | Not Started
T006 | Phase 1 | Stakeholder Mapping | Conduct stakeholder interviews/workshops | Run workshops with facility managers and sample end-users to validate requirements and gather edge cases. | Business Analyst | Medium | 3 | Identify roles and permissions matrix | Not Started
T007 | Phase 1 | Execution Roadmap | Build project timeline & milestones | Create schedule with requirements sign-off, design, dev sprints, testing, UAT, go-live milestones. | Project Manager | High | 2 | Compile functional requirements list | Not Started
T008 | Phase 1 | Execution Roadmap | Set up PPM/project tracking workspace | Configure ServiceNow PPM (or chosen PM tool) to track tasks, resources, risks, and sprint backlogs. | Project Manager | Medium | 1 | Build project timeline & milestones | Not Started
T009 | Phase 1 | Execution Roadmap | Risk register & mitigation plan | Identify project risks (scope creep, resource availability, integration issues) with mitigation owners. | Project Manager | Medium | 1 | Build project timeline & milestones | Not Started
T010 | Phase 1 | Sign-off | Requirements sign-off | Formal review and approval of requirements document by sponsor/stakeholders before development starts. | Sponsor / Product Owner | High | 1 | Conduct stakeholder interviews/workshops | Not Started
T011 | Phase 2 | Data Architecture | Design scoped application container | Create a new scoped app in ServiceNow for the Sports Hall Booking System to isolate tables, flows, and roles. | ServiceNow Developer | High | 1 | Requirements sign-off | Not Started
T012 | Phase 2 | Data Architecture | Design 'Facility' table | Fields: Facility Name, Location, Capacity, Sport Type, Operating Hours, Active flag, Image. | ServiceNow Developer | High | 2 | Design scoped application container | Not Started
T013 | Phase 2 | Data Architecture | Design 'Sports Booking' table | Fields: Date, Start Time, End Time, Facility (reference), Requested By (sys_user), Status (choice: Pending/Approved/Rejected/Cancelled), Notes. Decide against extending Task table; build fresh table. | ServiceNow Developer | High | 2 | Design 'Facility' table | Not Started
T014 | Phase 2 | Data Architecture | Define table relationships & reference qualifiers | Set up reference fields, related lists, and reference qualifiers (e.g., only active facilities selectable). | ServiceNow Developer | Medium | 1 | Design 'Sports Booking' table | Not Started
T015 | Phase 2 | Data Architecture | Create choice lists and dictionary overrides | Configure Status choices, labels, mandatory fields, default values, and field-level help text. | ServiceNow Developer | Medium | 1 | Design 'Sports Booking' table | Not Started
T016 | Phase 2 | Business Logic | Build 'Availability Check' subflow | Reusable subflow that queries for overlapping approved bookings for a facility/date/time and returns availability boolean. | ServiceNow Developer | High | 3 | Define table relationships & reference qualifiers | Not Started
T017 | Phase 2 | Business Logic | Build 'Send Notification' subflow | Reusable subflow to send email/portal notifications for booking status changes (submitted, approved, rejected, cancelled). | ServiceNow Developer | Medium | 2 | Design 'Sports Booking' table | Not Started
T018 | Phase 2 | Business Logic | Build main booking approval Flow | Flow triggered on record-created for Sports Booking: run availability check, initiate approval to facility manager, branch on approve/reject, update status, call notification subflow. | ServiceNow Developer | High | 4 | Build 'Availability Check' subflow, Build 'Send Notification' subflow | Not Started
T019 | Phase 2 | Business Logic | Implement Before Business Rule for double-booking prevention | Add a lightweight Before Insert/Update business rule as a final guard against invalid/overlapping records. | ServiceNow Developer | Medium | 1 | Build main booking approval Flow | Not Started
T020 | Phase 2 | Business Logic | Build auto-cancel scheduled job/flow | Scheduled flow to auto-cancel or expire pending requests not actioned within X days. | ServiceNow Developer | Low | 2 | Build main booking approval Flow | Not Started
T021 | Phase 2 | Business Logic | Document flow/subflow naming conventions | Create and apply a naming convention standard for flows, subflows, and actions; document in a design wiki. | ServiceNow Developer / Architect | Low | 1 | Build main booking approval Flow | Not Started
T022 | Phase 2 | Approvals & Notifications | Configure approval notification email templates | Design email templates for approval requests, approvals, rejections, cancellations with links back to the record/portal. | ServiceNow Developer | Medium | 2 | Build 'Send Notification' subflow | Not Started
T023 | Phase 2 | Approvals & Notifications | Configure wait/timer conditions | Add wait-for-condition or timer activities where needed (e.g., reminder before auto-cancel). | ServiceNow Developer | Low | 1 | Build auto-cancel scheduled job/flow | Not Started
T024 | Phase 2 | Security & Access | Define roles: sports_admin, facility_manager, user | Create custom roles and assign to appropriate user groups. | ServiceNow Admin | High | 1 | Create scoped application container | Not Started
T025 | Phase 2 | Security & Access | Configure ACLs on Sports Booking table | Create ACLs so users see/edit only their own bookings (Requested By = current user); facility managers see all records for their facilities. | ServiceNow Admin | High | 2 | Define roles: sports_admin, facility_manager, user | Not Started
T026 | Phase 2 | Security & Access | Configure ACLs on Facility table | Restrict facility configuration (create/edit/delete) to sports_admin role only. | ServiceNow Admin | Medium | 1 | Define roles: sports_admin, facility_manager, user | Not Started
T027 | Phase 2 | Security & Access | Set Service Portal page-level role restrictions | Mark booking/homepage as Public/employee-accessible; restrict admin/manager pages to relevant roles. | ServiceNow Admin | Medium | 1 | Configure ACLs on Sports Booking table | Not Started
T028 | Phase 2 | Security & Access | Enable field encryption for sensitive fields (if required) | Apply Field Encryption / Cross-Scope Decryption controls to any PII fields per data classification policy. | ServiceNow Admin / Security | Low | 1 | Configure ACLs on Sports Booking table | Not Started
T029 | Phase 3 | Interface Design | Define Service Portal theme & branding | Set up common theme, header, footer, and CSS/SCSS branding consistent with organizational identity. | UI/UX Developer | Medium | 2 | Requirements sign-off | Not Started
T030 | Phase 3 | Interface Design | Design 'Sports Booking' landing page | Build page with facility filter panel and dynamic calendar/list widget showing available slots using Service Portal Designer. | UI/UX Developer | High | 3 | Define Service Portal theme & branding, Design 'Sports Booking' table | Not Started
T031 | Phase 3 | Interface Design | Build 'Available Slots' widget | Custom widget querying the Booking table for real-time availability, with facility/date/time filters. | ServiceNow Developer | High | 3 | Design 'Sports Booking' landing page | Not Started
T032 | Phase 3 | Interface Design | Build booking request form widget | Form widget capturing facility, date, time slot, and user details, tied to the Sports Booking table; includes client-side validation. | ServiceNow Developer | High | 3 | Build 'Available Slots' widget | Not Started
T033 | Phase 3 | Interface Design | Apply accessibility & UX best practices | Verify color contrast, alt text on images, plain language labels, and appropriate input types (dropdowns, date/time pickers, reference fields). | UI/UX Developer | Medium | 1 | Build booking request form widget | Not Started
T034 | Phase 3 | Navigation Flow | Build 'My Bookings' page | Page listing the logged-in user's bookings (filtered by Requested By), with cancel/modify actions. | ServiceNow Developer | High | 2 | Build booking request form widget | Not Started
T035 | Phase 3 | Navigation Flow | Build cancel/modify booking widget logic | Widget server script to allow cancellation/modification within policy rules, triggering status update flow. | ServiceNow Developer | High | 2 | Build 'My Bookings' page | Not Started
T036 | Phase 3 | Navigation Flow | Build Admin/Manager console page | Dashboard for facility managers/admins to view all requests, approve/reject, and manage facility configuration. | ServiceNow Developer | High | 3 | Configure ACLs on Facility table, Build 'My Bookings' page | Not Started
T037 | Phase 3 | Navigation Flow | Configure portal navigation & menu links | Set up Header/Quick Links so users can navigate between Booking, My Bookings, and Admin pages based on role. | UI/UX Developer | Medium | 1 | Build Admin/Manager console page | Not Started
T038 | Phase 3 | Navigation Flow | Implement confirmation messages & feedback | Add success/error confirmation messages on submission, cancellation, and modification actions. | ServiceNow Developer | Low | 1 | Build cancel/modify booking widget logic | Not Started
T039 | Phase 3 | Component Specification | Document widget specifications | For each widget: define inputs, data sources (Table API/GlideRecord calls), outputs, and any client scripts/UI policies. | ServiceNow Developer | Low | 2 | Build Admin/Manager console page | Not Started
T040 | Phase 3 | Component Specification | Establish content taxonomy & labeling | Define consistent labels/categories across pages so users can easily find facilities and features. | UI/UX Developer | Low | 1 | Document widget specifications | Not Started
T041 | Phase 4 | Data Migration | Assess legacy booking data | Inventory legacy data sources and determine which historical bookings need migration vs. archiving. | Data/ServiceNow Developer | Medium | 2 | Design 'Sports Booking' table | Not Started
T042 | Phase 4 | Data Migration | Build Import Set & Transform Map | Configure Import Sets and Transform Maps to load historical/completed bookings into the new tables. | ServiceNow Developer | Medium | 3 | Assess legacy booking data | Not Started
T043 | Phase 4 | Data Migration | Define coalesce keys & suppress triggers | Set unique coalesce key (booking ID or composite) to avoid duplicates; disable business rules/notifications during import. | ServiceNow Developer | Medium | 1 | Build Import Set & Transform Map | Not Started
T044 | Phase 4 | Data Migration | Mark and audit migrated records | Add 'Migrated' checkbox field and log migration details/history in work notes or a legacy history table. | ServiceNow Developer | Low | 1 | Define coalesce keys & suppress triggers | Not Started
T045 | Phase 4 | Testing | Write unit test cases for flows | Use Flow Designer testing tools to unit test the booking, approval, and notification flows. | QA Engineer | High | 2 | Build main booking approval Flow | Not Started
T046 | Phase 4 | Testing | Build Automated Test Framework (ATF) regression suite | Cover booking creation, approval workflow, notifications, cancellations, and role-based access scenarios. | QA Engineer | High | 4 | Write unit test cases for flows | Not Started
T047 | Phase 4 | Testing | Conduct User Acceptance Testing (UAT) | Run UAT sessions with a facility manager and typical employee; capture and resolve usability issues. | Product Owner / QA | High | 3 | Build Automated Test Framework (ATF) regression suite | Not Started
T048 | Phase 4 | Testing | Fix defects from UAT feedback | Triage and resolve issues identified during UAT, focusing on usability and error messaging. | ServiceNow Developer | High | 3 | Conduct User Acceptance Testing (UAT) | Not Started
T049 | Phase 4 | Security & Compliance | Conduct ACL and access review | Verify only authorized roles can view/modify booking and facility data; confirm portal pages restrict correctly. | Security / ServiceNow Admin | High | 2 | Configure ACLs on Sports Booking table | Not Started
T050 | Phase 4 | Security & Compliance | Run Security Assessment / vulnerability scan | Execute ServiceNow Security Assessment or equivalent scan to check for scripting injection and other vulnerabilities. | Security Engineer | High | 2 | Conduct ACL and access review | Not Started
T051 | Phase 4 | Security & Compliance | Enable audit logging | Configure Record Producers/System Logs for auditing changes to bookings and facility configuration. | ServiceNow Admin | Medium | 1 | Conduct ACL and access review | Not Started
T052 | Phase 4 | Deployment | Prepare Update Sets for promotion | Package all configuration (tables, flows, ACLs, widgets, pages) into Update Sets for migration across environments. | ServiceNow Developer | High | 2 | Fix defects from UAT feedback | Not Started
T053 | Phase 4 | Deployment | Execute Dev → Test → Prod promotion | Follow change management process to move the application through environments with sign-off gates. | Release Manager | High | 2 | Prepare Update Sets for promotion | Not Started
T054 | Phase 4 | Deployment | Configure HTTPS/SSO for the portal | Ensure portal is served over HTTPS and integrate Single Sign-On if required by corporate policy. | ServiceNow Admin / IT Security | Medium | 1 | Execute Dev → Test → Prod promotion | Not Started
T055 | Phase 4 | Deployment | Go-live and hypercare support | Launch to production; monitor issues closely and provide hypercare support for the first 2 weeks. | Project Manager / Support Team | High | 2 | Execute Dev → Test → Prod promotion | Not Started

## Phase 1 - Requirements
Task ID | Phase | Workstream | Task | Description / Acceptance Criteria | Owner Role | Priority | Estimated Effort (days) | Dependencies | Status
T001 | Phase 1 | Business Objectives | Define business objectives & success metrics | Document goals: self-service booking, reduced admin overhead, improved facility utilization. Define KPIs (e.g., usage %, satisfaction score). | Business Analyst | High | 2 | - | Not Started
T002 | Phase 1 | Business Objectives | Define booking policy rules | Agree scope rules such as max advance booking window (X days), booking limits per user, cancellation windows. | Business Analyst / Sponsor | High | 1 | Define business objectives | Not Started
T003 | Phase 1 | Functional Scope | Compile functional requirements list | Document all required features: facility search/browse, real-time availability calendar, booking form, multi-stage approval, notifications, My Bookings (view/cancel/modify), admin console. | Business Analyst | High | 3 | Define business objectives | Not Started
T004 | Phase 1 | Functional Scope | Prioritize features into MVP vs later phases | Rank features by business value and feasibility; agree MVP scope for go-live. | Product Owner | Medium | 1 | Compile functional requirements list | Not Started
T005 | Phase 1 | Stakeholder Mapping | Identify roles and permissions matrix | Map roles: end-users (students/staff), facility managers/approvers, system administrators, IT support. Document needs, permissions, and RACI. | Business Analyst | High | 2 | Compile functional requirements list | Not Started
T006 | Phase 1 | Stakeholder Mapping | Conduct stakeholder interviews/workshops | Run workshops with facility managers and sample end-users to validate requirements and gather edge cases. | Business Analyst | Medium | 3 | Identify roles and permissions matrix | Not Started
T007 | Phase 1 | Execution Roadmap | Build project timeline & milestones | Create schedule with requirements sign-off, design, dev sprints, testing, UAT, go-live milestones. | Project Manager | High | 2 | Compile functional requirements list | Not Started
T008 | Phase 1 | Execution Roadmap | Set up PPM/project tracking workspace | Configure ServiceNow PPM (or chosen PM tool) to track tasks, resources, risks, and sprint backlogs. | Project Manager | Medium | 1 | Build project timeline & milestones | Not Started
T009 | Phase 1 | Execution Roadmap | Risk register & mitigation plan | Identify project risks (scope creep, resource availability, integration issues) with mitigation owners. | Project Manager | Medium | 1 | Build project timeline & milestones | Not Started
T010 | Phase 1 | Sign-off | Requirements sign-off | Formal review and approval of requirements document by sponsor/stakeholders before development starts. | Sponsor / Product Owner | High | 1 | Conduct stakeholder interviews/workshops | Not Started

## Phase 2 - Backend Dev
Task ID | Phase | Workstream | Task | Description / Acceptance Criteria | Owner Role | Priority | Estimated Effort (days) | Dependencies | Status
T011 | Phase 2 | Data Architecture | Design scoped application container | Create a new scoped app in ServiceNow for the Sports Hall Booking System to isolate tables, flows, and roles. | ServiceNow Developer | High | 1 | Requirements sign-off | Not Started
T012 | Phase 2 | Data Architecture | Design 'Facility' table | Fields: Facility Name, Location, Capacity, Sport Type, Operating Hours, Active flag, Image. | ServiceNow Developer | High | 2 | Design scoped application container | Not Started
T013 | Phase 2 | Data Architecture | Design 'Sports Booking' table | Fields: Date, Start Time, End Time, Facility (reference), Requested By (sys_user), Status (choice: Pending/Approved/Rejected/Cancelled), Notes. Decide against extending Task table; build fresh table. | ServiceNow Developer | High | 2 | Design 'Facility' table | Not Started
T014 | Phase 2 | Data Architecture | Define table relationships & reference qualifiers | Set up reference fields, related lists, and reference qualifiers (e.g., only active facilities selectable). | ServiceNow Developer | Medium | 1 | Design 'Sports Booking' table | Not Started
T015 | Phase 2 | Data Architecture | Create choice lists and dictionary overrides | Configure Status choices, labels, mandatory fields, default values, and field-level help text. | ServiceNow Developer | Medium | 1 | Design 'Sports Booking' table | Not Started
T016 | Phase 2 | Business Logic | Build 'Availability Check' subflow | Reusable subflow that queries for overlapping approved bookings for a facility/date/time and returns availability boolean. | ServiceNow Developer | High | 3 | Define table relationships & reference qualifiers | Not Started
T017 | Phase 2 | Business Logic | Build 'Send Notification' subflow | Reusable subflow to send email/portal notifications for booking status changes (submitted, approved, rejected, cancelled). | ServiceNow Developer | Medium | 2 | Design 'Sports Booking' table | Not Started
T018 | Phase 2 | Business Logic | Build main booking approval Flow | Flow triggered on record-created for Sports Booking: run availability check, initiate approval to facility manager, branch on approve/reject, update status, call notification subflow. | ServiceNow Developer | High | 4 | Build 'Availability Check' subflow, Build 'Send Notification' subflow | Not Started
T019 | Phase 2 | Business Logic | Implement Before Business Rule for double-booking prevention | Add a lightweight Before Insert/Update business rule as a final guard against invalid/overlapping records. | ServiceNow Developer | Medium | 1 | Build main booking approval Flow | Not Started
T020 | Phase 2 | Business Logic | Build auto-cancel scheduled job/flow | Scheduled flow to auto-cancel or expire pending requests not actioned within X days. | ServiceNow Developer | Low | 2 | Build main booking approval Flow | Not Started
T021 | Phase 2 | Business Logic | Document flow/subflow naming conventions | Create and apply a naming convention standard for flows, subflows, and actions; document in a design wiki. | ServiceNow Developer / Architect | Low | 1 | Build main booking approval Flow | Not Started
T022 | Phase 2 | Approvals & Notifications | Configure approval notification email templates | Design email templates for approval requests, approvals, rejections, cancellations with links back to the record/portal. | ServiceNow Developer | Medium | 2 | Build 'Send Notification' subflow | Not Started
T023 | Phase 2 | Approvals & Notifications | Configure wait/timer conditions | Add wait-for-condition or timer activities where needed (e.g., reminder before auto-cancel). | ServiceNow Developer | Low | 1 | Build auto-cancel scheduled job/flow | Not Started
T024 | Phase 2 | Security & Access | Define roles: sports_admin, facility_manager, user | Create custom roles and assign to appropriate user groups. | ServiceNow Admin | High | 1 | Create scoped application container | Not Started
T025 | Phase 2 | Security & Access | Configure ACLs on Sports Booking table | Create ACLs so users see/edit only their own bookings (Requested By = current user); facility managers see all records for their facilities. | ServiceNow Admin | High | 2 | Define roles: sports_admin, facility_manager, user | Not Started
T026 | Phase 2 | Security & Access | Configure ACLs on Facility table | Restrict facility configuration (create/edit/delete) to sports_admin role only. | ServiceNow Admin | Medium | 1 | Define roles: sports_admin, facility_manager, user | Not Started
T027 | Phase 2 | Security & Access | Set Service Portal page-level role restrictions | Mark booking/homepage as Public/employee-accessible; restrict admin/manager pages to relevant roles. | ServiceNow Admin | Medium | 1 | Configure ACLs on Sports Booking table | Not Started
T028 | Phase 2 | Security & Access | Enable field encryption for sensitive fields (if required) | Apply Field Encryption / Cross-Scope Decryption controls to any PII fields per data classification policy. | ServiceNow Admin / Security | Low | 1 | Configure ACLs on Sports Booking table | Not Started

## Phase 3 - UI-UX Dev
Task ID | Phase | Workstream | Task | Description / Acceptance Criteria | Owner Role | Priority | Estimated Effort (days) | Dependencies | Status
T029 | Phase 3 | Interface Design | Define Service Portal theme & branding | Set up common theme, header, footer, and CSS/SCSS branding consistent with organizational identity. | UI/UX Developer | Medium | 2 | Requirements sign-off | Not Started
T030 | Phase 3 | Interface Design | Design 'Sports Booking' landing page | Build page with facility filter panel and dynamic calendar/list widget showing available slots using Service Portal Designer. | UI/UX Developer | High | 3 | Define Service Portal theme & branding, Design 'Sports Booking' table | Not Started
T031 | Phase 3 | Interface Design | Build 'Available Slots' widget | Custom widget querying the Booking table for real-time availability, with facility/date/time filters. | ServiceNow Developer | High | 3 | Design 'Sports Booking' landing page | Not Started
T032 | Phase 3 | Interface Design | Build booking request form widget | Form widget capturing facility, date, time slot, and user details, tied to the Sports Booking table; includes client-side validation. | ServiceNow Developer | High | 3 | Build 'Available Slots' widget | Not Started
T033 | Phase 3 | Interface Design | Apply accessibility & UX best practices | Verify color contrast, alt text on images, plain language labels, and appropriate input types (dropdowns, date/time pickers, reference fields). | UI/UX Developer | Medium | 1 | Build booking request form widget | Not Started
T034 | Phase 3 | Navigation Flow | Build 'My Bookings' page | Page listing the logged-in user's bookings (filtered by Requested By), with cancel/modify actions. | ServiceNow Developer | High | 2 | Build booking request form widget | Not Started
T035 | Phase 3 | Navigation Flow | Build cancel/modify booking widget logic | Widget server script to allow cancellation/modification within policy rules, triggering status update flow. | ServiceNow Developer | High | 2 | Build 'My Bookings' page | Not Started
T036 | Phase 3 | Navigation Flow | Build Admin/Manager console page | Dashboard for facility managers/admins to view all requests, approve/reject, and manage facility configuration. | ServiceNow Developer | High | 3 | Configure ACLs on Facility table, Build 'My Bookings' page | Not Started
T037 | Phase 3 | Navigation Flow | Configure portal navigation & menu links | Set up Header/Quick Links so users can navigate between Booking, My Bookings, and Admin pages based on role. | UI/UX Developer | Medium | 1 | Build Admin/Manager console page | Not Started
T038 | Phase 3 | Navigation Flow | Implement confirmation messages & feedback | Add success/error confirmation messages on submission, cancellation, and modification actions. | ServiceNow Developer | Low | 1 | Build cancel/modify booking widget logic | Not Started
T039 | Phase 3 | Component Specification | Document widget specifications | For each widget: define inputs, data sources (Table API/GlideRecord calls), outputs, and any client scripts/UI policies. | ServiceNow Developer | Low | 2 | Build Admin/Manager console page | Not Started
T040 | Phase 3 | Component Specification | Establish content taxonomy & labeling | Define consistent labels/categories across pages so users can easily find facilities and features. | UI/UX Developer | Low | 1 | Document widget specifications | Not Started

## Phase 4 - Migration-Test-Sec
Task ID | Phase | Workstream | Task | Description / Acceptance Criteria | Owner Role | Priority | Estimated Effort (days) | Dependencies | Status
T041 | Phase 4 | Data Migration | Assess legacy booking data | Inventory legacy data sources and determine which historical bookings need migration vs. archiving. | Data/ServiceNow Developer | Medium | 2 | Design 'Sports Booking' table | Not Started
T042 | Phase 4 | Data Migration | Build Import Set & Transform Map | Configure Import Sets and Transform Maps to load historical/completed bookings into the new tables. | ServiceNow Developer | Medium | 3 | Assess legacy booking data | Not Started
T043 | Phase 4 | Data Migration | Define coalesce keys & suppress triggers | Set unique coalesce key (booking ID or composite) to avoid duplicates; disable business rules/notifications during import. | ServiceNow Developer | Medium | 1 | Build Import Set & Transform Map | Not Started
T044 | Phase 4 | Data Migration | Mark and audit migrated records | Add 'Migrated' checkbox field and log migration details/history in work notes or a legacy history table. | ServiceNow Developer | Low | 1 | Define coalesce keys & suppress triggers | Not Started
T045 | Phase 4 | Testing | Write unit test cases for flows | Use Flow Designer testing tools to unit test the booking, approval, and notification flows. | QA Engineer | High | 2 | Build main booking approval Flow | Not Started
T046 | Phase 4 | Testing | Build Automated Test Framework (ATF) regression suite | Cover booking creation, approval workflow, notifications, cancellations, and role-based access scenarios. | QA Engineer | High | 4 | Write unit test cases for flows | Not Started
T047 | Phase 4 | Testing | Conduct User Acceptance Testing (UAT) | Run UAT sessions with a facility manager and typical employee; capture and resolve usability issues. | Product Owner / QA | High | 3 | Build Automated Test Framework (ATF) regression suite | Not Started
T048 | Phase 4 | Testing | Fix defects from UAT feedback | Triage and resolve issues identified during UAT, focusing on usability and error messaging. | ServiceNow Developer | High | 3 | Conduct User Acceptance Testing (UAT) | Not Started
T049 | Phase 4 | Security & Compliance | Conduct ACL and access review | Verify only authorized roles can view/modify booking and facility data; confirm portal pages restrict correctly. | Security / ServiceNow Admin | High | 2 | Configure ACLs on Sports Booking table | Not Started
T050 | Phase 4 | Security & Compliance | Run Security Assessment / vulnerability scan | Execute ServiceNow Security Assessment or equivalent scan to check for scripting injection and other vulnerabilities. | Security Engineer | High | 2 | Conduct ACL and access review | Not Started
T051 | Phase 4 | Security & Compliance | Enable audit logging | Configure Record Producers/System Logs for auditing changes to bookings and facility configuration. | ServiceNow Admin | Medium | 1 | Conduct ACL and access review | Not Started
T052 | Phase 4 | Deployment | Prepare Update Sets for promotion | Package all configuration (tables, flows, ACLs, widgets, pages) into Update Sets for migration across environments. | ServiceNow Developer | High | 2 | Fix defects from UAT feedback | Not Started
T053 | Phase 4 | Deployment | Execute Dev → Test → Prod promotion | Follow change management process to move the application through environments with sign-off gates. | Release Manager | High | 2 | Prepare Update Sets for promotion | Not Started
T054 | Phase 4 | Deployment | Configure HTTPS/SSO for the portal | Ensure portal is served over HTTPS and integrate Single Sign-On if required by corporate policy. | ServiceNow Admin / IT Security | Medium | 1 | Execute Dev → Test → Prod promotion | Not Started
T055 | Phase 4 | Deployment | Go-live and hypercare support | Launch to production; monitor issues closely and provide hypercare support for the first 2 weeks. | Project Manager / Support Team | High | 2 | Execute Dev → Test → Prod promotion | Not Started